## CRs
Complexity | Title | Description | Owner | Assigned To | Status | Submitter Id | Module Name | Project Phase | Actual Closed Date (MM/DD/YYYY) | Priority | Target Date (MM/DD/YYYY) | Submitted in Project Phase | Private | Resolution | UID | Reconsideration Criteria | Actual Effort | Planned Effort | Impact Of Change | CR Type | Submitted Date (MM/DD/YYYY) | Notes
Simple | Update the View Flight Inventory page to support viewing of inventory for a range of days. | For Admin module, View Flight Inventory page right now displays only current day's scheduled flights. The client wants to support viewing of scheduled flights inventory for a range of days. It is proposed to add two date fields that can be selected by the Admin to provide a range of dates over which the schedules should be displayed. If no date is selected in both, only the current day's schedules are displayed (Default). If only one date is selected, then the other date is defaulted to current date. | [17 empty] | Minor
Simple | Scheduling of a Flight after 3 hours of arrival | In Admin module, it is required to update the Add Schedule feature. A flight should not be allowed to be scheduled for a time and date if it has already been scheduled for that duration. Also a Flight can only be scheduled 3 hours after its currently scheduled arrival and for adding/editing a schedule, the time to departure should be atleast 3 hrs ahead of current time. For Example, if a flight is scheduled on 5 May for 16:00 to 18:00 hrs, on any route, then it can only be scheduled at 21:00 hours or after on that day. If Admin tries to schedule the flight that is not 3 hrs ahead from current time or its last arrival then he should be shown an error message and the operation should not be completed
Complex | Redeem Miles to buy ticket-Registered user | Allow registered users to redeem their happy miles while booking a ticket. When registered user reaches the confirmation page, in the booking process, he should be provided a check box, to opt for paying by miles. He has to specify the number of miles to redeem. An amount equal to the number of miles being redeemed will be deducted from the final amount charged and that will also be deducted from his miles balance post the payment process is completed successfully. The miles to redeem cannot be greater than cost of the ticket. When a ticket is booked with redemption of miles, then on cancellation of this ticket, the miles will not be refunded back.
Medium | Return flight departs atleast after 2 hours | In the current HappyTrip application it has been observed that user can book a return flight, irrespective of user's arrival & next flight's departure time. So there is a requirement to enhance the application such that when a user searches for a return flight and makes selections, it should be verified that the return flight selected departs at least two hours after the arrival of the onward flight. Hence user can view this flight in search results but he cannot select this flight for booking return journey as it is departing in less than 2 hours from the time since the user arrived. For example, if user selects to search for return flights on route Bangalore -Chennai and if the flight from Bangalore to Chennai arrives at 1200 hrs then all the flights returned for Chennai-Bangalore route that depart before 1400 hrs cannot be selected
Medium | Allow a non-registered user to cancel a booked flight using the booking reference number. | In the current HappyTrip application it has been observed that non-registered user cannot cancel a booking. We want to enhance the application by adding the cancellation of ticket feature for a guest user as well. This page will ask for a booking reference number that is generated during booking after payment is successful. The guest user needs to provide this reference number to retreive the booking details and from details page he can choose to cancel the ticket. This module is accessible to everyone from home page, top right links. A registered user can also use this feature for cancellation of his bookings, by providing the booking reference number.
Simple | While scheduling a flight, ask the admin to enter cost of only the class that is supported by the chosen flight | Currently in the application if a flight is added with only one of class capacity, the cost for both Economy and business are mandatory for scheduling every flight, even if they do not have a particular class. Now we are changing the application wherein, while scheduling a flight, the application will ask the admin to enter cost of only the class that is supported by the chosen flight.Hence the class not added onto the flight will not prompt for any cost to be entered and its field will also not be displayed
Medium | Autosuggest refined to show only routes that have schedules existing | It has been decided to modify the autosuggest feature in the search flights module. While searching for a flight, when a user selects a city in the “From” text box, in the “To” text box system should provide autosuggest list, of only the scheduled flights whose origin is same as "From" city. For example: If there are schedules existing between Bangalore-Kolkatta and no schedules existing between Bangalore-Kanchipuram, then when user enters Bangalore in the From City text box, and enters letter "K" in the To city text box, the autosuggest should display only Kolkatta as an option and not Kanchipuram.
Medium | Add support for re-scheduling a flight This should be possible even after the departure time, as a flight could have been delayed or canceled | In the Admin module it is required to add support for re-scheduling a flight. The rescheduling should be possible even after the departure time for the flight has passed, as a flight could have been delayed or cancelled. From View Inventory page we will provide a link "Reschedule" to reschedule the flight to a different date/time. The rescheduling page provides following data to be edited: •Distance •Departure Date •Departure Time •Arrival Date •Arrival Time •Cost of classes present in the flight Admin can make the modifications, and click Edit to reschedule flight. The flight rescheduling follows same rules & policies as adding of a new schedule.
Complex | Support cancellation of a scheduled flight. All the passengers who have booked tickets on the flight should get a full refund. | In the Admin module it is required to add support for cancelling a scheduled flight. The cancellation should be possible even after the departure time for the flight has passed, as a flight could have been delayed or cancelled. From View Inventory page we will provide a link "Cancel" to cancel the schedule of the flight. On clicking the Cancel link, the application will ask for a confirmation of Cancel Flight. If admin confirms it, then flight schedule should be removed from the inventory and all the passengers who have booked tickets on that flight should get a full refund (including insurance). Also this flight should now be available to add a new schedule within the same time + 3 hours from its arrival time that has been cancelled now. For example, if the flight was scheduled between Bangalore-Chennai for 1200 hrs to 1300 hrs then this flight schedule on cancellation, can now have a new schedule added anytime between 1200 hrs to 1600 hrs.
Simple | Support Modification of search criteria for search flights ,for all users. | In HappyTrip it has been observed that once user gets search results, he cannot modify search criteria. It is required to support Modification of search criteria for search flights ,for all users. A user can modify the search criteria from any of the subsequent pages by clicking Modify Search link, until he has made the payment. on clicking Modify search link, user should be able to come back to home page and modify any or all of search criteria and the search functionality will be started afresh to show the updated results.
Note on B1: Mandatory Field
Note on C1: Mandatory Field
Note on D1: Mandatory Field
Note on E1: Mandatory Field
Note on F1: Mandatory Field
Note on G1: Mandatory Field
Note on V1: NonMandatory Field. If submitted date is empty, current date will be considered as submitted date

## Bugs
Bug No. | Summary | Description
Bug1 | With multiple passengers, if registered user books & then cancels a ticket. The insurance calculation for deduction is not correct. | Pre-condition: A scheduled flight exists on the route Bangalore-Chennai, but there is no flight on route Chennai-Bangalore, for today Steps to reproduce: 1. Go to home page, as registered user, select return flight on Chennai to Bangalore, for today 2. Select 2 Adults, 2 Child, 1 Infant, for business class 3. From search results, select the flight for Bangalore-Chennai 4. Add passengers details and confirm. 5. Make payment 6. From My Trips, Cancel this booking. Expected result: The refund calculated is based on business ticket cost with, insurance and cancellation charges deducted. Here insurance calculation is based on the business class cost Actual Result: The refund is calculated based on, insurance calculated on basis of the economy cost
Bug 2 | Bookings made where HappyMiles are earned, do not appear in the My Trips page | Pre-condition: A scheduled flight exists on the route Bangalore-Chennai, for today, and this flight belongs to an airline which is registered in HappyMiles (Indigo) Steps to reproduce: 1. Go to home page, as registered user, select one-way flight on Bangalore to Chennai, for today 2. Select from search results, the flight that belongs to airline registered with HappyMiles 3. Click on Book button 4. Add passengers details and confirm. 5. Make payment 6. From View/Edit Page observe the Miles accumulated 7. Go to My Trips and observe the results Expected result: The booking made, where happymiles are earned, is visible and Miles are added in the user account Actual Result: The miles are added but the booking does not appear in the My Trips page